## Sheet1
Schedule Collecting (Sharepoint tool example) |  | Legend
Goal: Allow each SME/Architect to list his activities inside the milestones and phases. |  | ██ Phase ██ Group ██ Dependency
Context: There are 4 phases (Start-up, Planning, Execution and Closeout). SMEs may only pay attention to Planning and Execution and eventually closeout. |  | ██ VP Milestones ██ Major Milestone
How works: Each SME may fulfill an independent sheet. Later we compile!
Feel free to:
- Include activities
- Update Major Milestones
- Include dependencies (if you don't know the "source name", leave blank.
Start-up
+ GENERAL ---------------------------------------------------------------------------------------
TYPE | DESCRIPTION | DATE | Resource | Predecessor
TASK | PM engaged | 2010-09-28 | ProjectOffice | -
DEPENDENCY | DEPENDENCY: Full Team engaged | 2010-10-17 | ProjectOffice | 11
TASK | Grant access to Customer's Team room |  | PM | 12
TASK | Support each SME to review documentation | 2010-10-18 | PM | 11
Planning
+ SHAREPOINT ---------------------------------------------------------------------------------------
TYPE | DESCRIPTION | DATE | Resource | Predecessor
<task> | <insert activities here...> | <date> | <role> | <rowid>
<task> | <insert activities here...> | <date> | <role> | <rowid>
<task> | <insert activities here...> | <date> | <role> | <rowid>
MAJOR MILESTONE | MILESTONE: Phase Startup Complete | <insert dates> | - | -
MAJOR MILESTONE | MILESTONE: Project Plan Approval | <insert dates> | - | -
MAJOR MILESTONE | MILESTONE: Transformation Plan Activities Complete | <insert dates> | - | -
MAJOR MILESTONE | MILESTONE: Transformation Plan Baselined and Approved by Customer | <insert dates> | - | -
VP MILESTONE | MILESTONE: Detailed Transition Plan | 2010-10-05 | - | -
Execution
+ SHAREPOINT ---------------------------------------------------------------------------------------
TYPE | DESCRIPTION | DATE | Resource | Predecessor
<task> | <insert activities here...> | <date> | <role> | <rowid>
MAJOR MILESTONE | MILESTONE: Server inventory approved | <insert dates> | - | -
MAJOR MILESTONE | MILESTONE: Servers for new farm provisioned. | <insert dates> | - | -
MAJOR MILESTONE | MILESTONE: Software for new farm installed (MOSS, SQL, 3rd party) | <insert dates> | - | -
MAJOR MILESTONE | MILESTONE: Network connectivity successfully tested | <insert dates> | - | -
VP MILESTONE | MILESTONE: Infrastructure Ready | 2011-02-08 | - | -
TYPE | DESCRIPTION | DATE | Resource | Predecessor
<task> | <insert activities here...> | <date> | <role> | <rowid>
MAJOR MILESTONE | MILESTONE: Content migrated for old production farm to new production farm | <insert dates> | - | -
MAJOR MILESTONE | MILESTONE: Custom code migrated from old production farm to new production farm | <insert dates> | - | -
MAJOR MILESTONE | MILESTONE: Integrated test completed | <insert dates> | - | -
MAJOR MILESTONE | MILESTONE: Steady-State services turnover commencement completed | <insert dates> | - | -
VP MILESTONE | MILESTONE: Sharepoint Implementation Complete | 2011-05-03 | - | -
Closeout
TYPE | DESCRIPTION | DATE | Resource | Predecessor
<task> | <insert activities here...> | <date> | <role> | <rowid>
MAJOR MILESTONE | MILESTONE: Perform Steady State Handoff Completed |  |  | -
DEPENDENCY | DEPENDENCY: Transformation Closeout Reports Approved | <when> | ProjectOffice
VP MILESTONE | MILESTONE: Project Completed