## Sheet1
Project Schedule
Activity | Total Effort | Responsible | Status
Analyze the router config | 1 hour | John | done
Create static routes | 10 minutes | John | done
Create crypto map | 10 minutes | John | done
Create access-list | 30 minutes | John | done
Open ticket | 30 minutes | John | done
Coordinate with firewall team | 30 minutes | John | done
Checking basic connectivity | 2 hours | John | done
Checking connectivity between all servers - | ? hours – | John | in progress
Dependencies | Who
pre-share key | Supplier X